## FY26-27 Roadmap
| 2025 | [5 empty] | 2026 | [11 empty] | 2027
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
SPARROW | Q1 SEP: Sparrow Installation Manual; Q2 NOV: SPARROW LAUNCH
|  |  | PyTorch Desktop Client |  |  | SPARROW STUDIO Development |  |  |  | SPARROW STUDIO Launch | SPARROW STUDIO MAC&Linux Version
[7 empty] | XBee Testing |  | SPARROW Go Rollout
|  | Dashboard Migration |  |  | Pi SPARROW | [5 empty] | PI SPARROW MANUAL |  | Pi SPARROW Launch
|  | Acoustic model v1 |  |  |  |  | Sparrow Software Simplification
Sparrow V3 Development
ROBIN | Q1 AUG: Robin Dev + Testing; Q4 MAY: Robin Installation Manual; Q1 AUG: ROBIN Open Sourcing; Q2 NOV: Testing; Q2 DEC: ROBIN LAUNCH
CONDOR | Q1 AUG: Data Annotation
FIRE MODEL UPDATE AND SUPPORT
|  | Fire Triangulation v1 |  |  | CONDOR V1 Handoff |  |  |  |  | Fire Localization | Archive Data Pipeline
[5 empty] | CONDOR UX UI Re-Skin |  |  |  |  | OCR For Camera Values
Online Inference
|  | Camera PTZ | [11 empty] | Camera PTZ
Water | Q2 OCT: Water SPARROW Development; Q4 MAY: Testing; Q4 JUN: Deployment
[7 empty] | Hardware Position Configuration |  |  | Buoy Redesign
Hydrophone integration and testing
Water ROBIN Development
Whale Model
Weather | Q4 JUN: Weather SPARROW Development; Q2 NOV: Testing
Sensor integration and testing
Deployments SPARROW GO | Q4 APR: CHESTER ZOO - BONGO
RHINO - South Africa
Elephants - Indonesia
CHESTER ZOO - Badgers
CHESTER ZOO - UGANDA
Natural England - Badgers
Deployments | Q1 AUG: Salonga Part 1 (6SPW + 30WFCAM) DELAYED BUT ON TRACK; Q1 AUG: KEW Gardens Brazil; Q3 JAN: Salonga + Virunga Part 2 (7SPW + 35WFCAM)
|  | Gombe Test Unit (1SPW+4WFCAM) | [6 empty] | Gombe Deployment (5SPW+26WFCAM) |  |  |  |  | KEW Gardens UK
|  |  |  | PERU Deployment in Los Amigos |  |  |  | CHESTER ZOO - Pangolin |  | WATER SPARROW (BLUE) - Puget Sound Deployment (1SPW + 1RBN)
|  |  | IGNITE? (3 Fancy looking SPARROWS) |  |  |  |  | CHESTER ZOO |  |  | Instituto Cerrados 3 Cams / Condor Pipeline |  | WATER SPARROW (BLUE) - NOAA Sound Deployment (1SPW)
Scotland Deplyoment (TBD) *NEED ROBIN*
|  | Colombia Deployment and Retrofit SINCHI/El Silencio |  |  | Uruguay Shipping of Components (5SPW + 30WFCAM + 6RBN + 6CAMTRAP+PI Builds) |  |  | CHESTER ZOO - BONGO |  |  | Colombia Deployment and Retrofit SINCHI/El Silencio
DONE

## SPARROW SPRINT BACKLOG
Prioty | Sprint | Area | Work Item | Lead | Collaborators | Status
| March | Hardware / Design | Define Water SPARROW hardware architecture & components | Bruno | Carl, Miao
| March | Build / Test | End-to-end Water SPARROW build & testing | Bruno | Carl, Miao
| March | Client Software | Water SPARROW client & sensor support | Carl
| March | Dashboard | Water SPARROW dashboard & REST APIs | Carl
| April | Deployment (One Thing) | Deploy Water SPARROW (SMRU buoy) | Bruno | Carl, Miao, Manolo
| April | Manufacturing | Buoy ring redesign & manufacturing | Bruno
| April | Deployment | Field deployment & readiness (SMRU) | Bruno | Carl, Miao
| April | Field Test | Deploy SPARROW to Chester Zoo | Carl
| April | Infrastructure | Migrate Water SPARROW dashboard to Azure | Carl |  |  | Status
| March | SPARROW Studio | OWL integration into SPARROW Studio | Daniel | Carl, Miao |  | Done
| March | SPARROW Studio | Finalize SPARROW Studio release & compliance | Carl | Bruno |  | On Track
| March | SPARROW Studio | Live camera processing & dark filter | Carl
| March | SEO / Platform | MegaDetector / OWL positioning & SEO groundwork | Daniel | Bruno, Miao |  | Done
| April | SPARROW Studio | SPARROW Studio beta testing | Zhongqi |  |  | Done
| April | Models | OWL model expansion & improvement | Zhongqi | Daniel Chacón |  | Done
| April | Compliance | Ensure SPARROW Studio ships without compliance blockers | Carl | Bruno, Amy
| March | Bioacoustics | Humboldt dataset paper | Zhongqi | Daniela Ruiz |  | Delayed
| April | Bioacoustics | Orca model development | Zhongqi | Daniela |  | On Track
| April | Bioacoustics | General bioacoustics model development | Zhongqi | Daniela |  | Pospone
|  |  |  | Daniela |  |  | Pospone
Done
Done
Done
Done
Done
Done

## SPARROW Installation Requests
Continent | Country/Region | Location | Partner Organizations | STATUS | Deployment Type | Timeline | Hardware Details | Estimated Total Cost (USD) | Notes | DevOps ID | Carl comments | Miao Comments
Africa | DRC | Salonga Part 1 | Salonga National Park | ON TRACK Part 1 on the way to SALONGA | Self-deploy | Before End FY26? | Part 1 6 Sparrows 30 WiFi Cams | 25000 | Shipment routed via EU/Spain; As of 4/9/25, equipment expected soon; Bruno meeting Paulo week of April 13. | 341227
Africa | DRC | Salonga Part 2 | Virunga National Park + Salonga National Park | At risk / likely descoped from Virunga | Self-deploy | Before End FY26? | Part 2 6 Sparrow 30 WiFi Cams | TBD | Virunga likely dropped due to conflict; possible redeploy of at least one unit to another park.
Africa | Kenya | Masaai Mara | Smithsonian National Zoo | Scoping | Self-deploy | TBD | TBD | TBD | Need to follow up with Smithsonian DC
Africa | Tanzania | Gombe | Jane Goodall Institute | Waiting on partner timing | Self-deploy | Test unit Before end of March 2026 - Rest Before End FY26 | 1 Test Unit, w 4 Cams - 5 more later on once they have tested the first one (30 WiFi cams) | 30000 | Parts shipped but battery was omitted; no firm timeline; partner dictates deployment timing. | 406972
Africa | UK | Chester Zoo Bongo | Chester Zoo | On Track | UK support - they deploy | Before May FY26 | TBD | 6000 | on track | 447849
Africa | UK | Chester Zoo Pangolin | Chester Zoo | On Track | UK support - they deploy | Before May FY26 | TBD | 6000 | on track; Panglin SPARROW deployed in zoo. Waiting for redeployment. | 447885
Africa | UK | Ol Pejeta White Rhino | Ol Pejeta | On Track | UK support - they deploy | Before May FY26 | TBD | 6000 | Partner waiting to hear from us | 452642
Antarctica | Antarctica | Chile Base | CONAF | On hold pending Water Sparrow | High | Winter Sparrow work paused until Water Sparrow is proven; thermal and battery issues remain. | On hold pending Water Sparrow | High | Winter Sparrow work paused until Water Sparrow is proven; thermal and battery issues remain.
Antarctica | Antarctica | Uruguay Base | TBD | Early scoping, no partner yet | High | Bruno plans to speak to Air Force contacts; no partner currently in place. | Early scoping, no partner yet | High | Bruno plans to speak to Air Force contacts; no partner currently in place.
Asia | Indonesia | Indonesia | University College London - Dan Giles | Scoping | Self-deploy | TBD | TBD | TBD | Waiting for Robin to be fully tested and documented.
Asia | Japan | Japanese Southern Alps (Mt. Senmai-dake) | National Institute for Environmental Studies (NIES) | Approved | Self-deploy | Q4 2026 | SPARROW + ROBIN units |  | Bruno synced end of March; project remains active but depends on Robin readiness and likely cold-weather hardware. | 485445
Europe | Greenland | Greenland | University College London - Dan Giles | Scoping | Self-deploy | TBD | TBD | TBD | Same Robin dependency, unsure we'll pursue this
Europe | Scotland | Scotland | Durrell Wildlife Conservation Trust | Scoping | on location assist | TBD | TBD | TBD | Deployment expected after Robin is finished; Carl may assist on-site.
Europe | UK | UK - North England | University College London - Dan Giles | Scoping | Self-deploy | TBD | TBD | TBD | Waiting for Robin to be fully tested and documented.
North America | USA | California - Condors | National Geographic + Condor Reserve | Installed | on location assist, continuous support | Done | 1 Sparrow 20 cams + 2 PTZ doing live video | 5000 | Equipment and cameras were left with partner, but cameras still not deployed; possible pay-to-play friction. | 392961
North America | USA | California - Turtles | National Geographic + Turtle Conservancy | Installed | on location assist, continuous support | Done | 1 Sparrow 20 cams + 1 Thermal Cam | 5000 | Equipment and cameras were left with partner, but cameras still not deployed; possible pay-to-play friction.
North America | USA | California, AlertCalifornia | UC San Diego, AlertCalifornia, Kern County | Installed | on location assist, continuous support | Done | 2 Main Brain Unit | 500 | on track | 392964
North America | USA | California, Channel Islands | National Park Service, Bay Area Environmental Research Institute (BAER) | Active | Self-deploy | TBD | TBD | TBD
North America | USA | California, UC Reserves | UC Natural Reserve System | Active | Self-deploy | TBD | Donate 1 SPARROW with multip0le ROBINs | TBD | Waiting on Pi Sparrow docs anddonation of one SPARROW and 5 Robins
North America | USA | Cascades, WA | Woodland Park Zoo | Active | on location assist | TBD | TBD | TBD | waiting on partner logistics | 379482
North America | USA | Des Moines, WA | MaST Center Aquarium / Highline College | Scoping | TBD | Target Dec 2026 | Underwater camera + hydrophone |  |  | 479407
North America | USA | Grand Canyon, AZ | Grand Canyon National Park | Scoping | TBD | TBD | TBD |  | Better suited to satellite or deforestation work. | 486798
North America | USA | Headwater streams | USGS NE Climate Adaptation Science Center | Waiting (On Robin) | Self-deploy | Target Jun 2026 | ROBIN units |  | Anthony/Amrita sourced | 376311
North America | USA | Microsoft Ignite | Microsoft (internal) | Done | On location | 45962 | Demo unit |  |  | 430565
North America | USA | Mt Rainier, WA | National Park Service | Water-level monitoring may not need a full Sparrow unit; Bruno is reviewing the one-pager. | TBD | Target Dec 2025 | TBD |  | Water-level monitoring may not need a full Sparrow unit; Bruno is reviewing the one-pager. | 405959
North America | USA | Notre Dame, IN | Notre Dame University | Scoping (Waiting) | TBD | Dec 2026 next steps | TBD |  | Laura sourced | 403147
North America | USA | Puget Sound, WA | SMRU | Active | on location assist | Before end of FY26 | SMRU buoy, GSM, solar panels, hydrophone | TBD | on track | 394083
North America | USA | Seattle, WA | Slalom | Complete | N/A (build partner) | Target Mar 2026 | Build plan for Sparrow assembly |  | done | 424062
North America | USA | Woodland Park Zoo | Woodland Park Zoo | Installed | on location assist | Done | 1 Sparrow 6 cams | 4000 | done | 340710
Oceania | New Zeland | New Zealand | Department of Conservation | Scoping | Self-deploy | TBD | TBD | TBD | Pospone until Robin is Ready
North America | Atlantic Ocean | Atlantic Ocean - Right Whales | NOAA; Woods Hole Oceanographic Institute | Scoping | Self-deploy | Before End FY26 | TBD | TBD | No agreements yet with NOAA | 388701
South America | Brazil | Atlantic Forest | Royal Botanical Gardens, Kew | Active | Self-deploy | Before End FY26 | List of parts to be sent, 1-2 sparrow donation, they will install rest | TBD | Partner is waitingfor equipment donation | 387033
South America | Brazil | Cerrado | Instituto Cerrados | Active | Self-deploy | Before end of FY26 | Donate 1 GSM camera | 2000 | They want Project CONDOR style alerts and monitoring. Fire season starts June 2026, so real results might be in soon. | 469692
South America | Colombia | Colombian Forests | Vigia Forestal | Scoping | on location assist, continuous support | Before End FY26? |  | TBD | No cost for us, covered by them. Postpone until Robin is Ready
South America | Colombia | Colombian Forests | SINCHI | Installed | on location assist, continuous support | Done | 2 Sparrow 8 Cams |  | Waiting on Pi Sparrow | 352457
South America | Colombia | Colombian Forests | Humboldt | On Track | self-deploy, continuous support | Before May FY26? | 2 Sparrows 30 Cams | 9000 | Pospone until Robin is Ready
South America | Colombia | El Silencio + Monos | Fundación Biodiversa Colombia + Universidad de los Andes | Installed | on location assist, continuous support | Done | 6 Sparrows 24 Cams | 20000 |  | 352455
South America | Peru | Los Amigos | ACCA - Asociación para la Conservación de la Cuenca Amazónica | Installed | on location assist, continuous support | Done | 1 complete sparrow unit 6 cameras and local sourcing for solar panels battery and Starlink | 4000 | Retrofit to be planned | 352458
South America | Peru | Peruvian Forests | SERNANP | Scoping | Self-deploy - Remote Support GUACAMAYA | Before End FY26? | 1 complete sparrow unit 4 cameras and local sourcing for solar panels battery and Starlink | 4000 | Retrofit to be planned
South America | Peru | Tambopata, Puna, Paracas | Smithsonian Center for Conservation & Sustainability | Scoping | Self-deploy | 2026-2027 | 3 Robin + 2 Sparrow units | 8000 | waiting for them to come back | 464112
South America | Peru | Wayqecha & Manu, Cusco | ACCA (Corine) | Scoping | Self-deploy or assist | Target Jun 2026 | 2 Sparrows + 30 Cams each |  | Retrofit to be planned | 466431
South America | Uruguay | Uruguay | TBD | Scoping | on location assist | Before End FY26 | Need Hardware for R&D + Possibly 6+ units in total plus 6 Robins |  | Waiting to finish prototyping ROBIN

## Sparrow Studio-PyTorch
SPARROW STUDIO / PYTORCH WILDLIFE - DevOps Status (April 2026)
DevOps ID | Epic Title | State | Assigned To | Principal Accountable | Start Date | Target Date | Description
502065 | SPARROW STUDIO | Active | Carl Chalmers | Zhongqi Miao | 2026-03-01 | 2026-12-31 | Desktop client for Sparrow/Pytorch solution
502066 | SPARROW Go | Active | Carl Chalmers | Zhongqi Miao | 2026-03-01 | 2026-12-31 | Cloud inferencing for 4G field cameras
481203 | PYTORCH WILDLIFE EXPANSION | Approved | Zhongqi Miao | Zhongqi Miao | 2025-07-01 | 2026-06-30 | Expansion of PyTorch Wildlife toolkit
430249 | PYTORCH SPARROW DASHBOARD Integration | Active | Bruno Demuro Segundo | Zhongqi Miao | 2024-07-01 | 2026-03-31 | No-code PyTorch for local/online + audio
SPARROW STUDIO (#502065) - User Stories
DevOps ID | Title | State | Type | Assigned To | Sprint
466546 | Local PytorchWildlife UI version 1 | Closed | User Story | Carl Chalmers
483375 | Add SpeciesNet to SPARROW Studio Desktop App | Closed | User Story | Carl Chalmers
483398 | Add HerdNet to SPARROW Studio Desktop App | Closed | User Story | Carl Chalmers
483400 | Add Hide bounding box toggle | Closed | User Story | Carl Chalmers
483402 | Updated model server/client for different pipelines | Closed | User Story | Carl Chalmers
483404 | Add model factory and interfaces for new models | Closed | User Story | Carl Chalmers
483407 | Add image annotation support (incl. additional classes) | Closed | User Story | Carl Chalmers
483410 | Add legal terms and conditions to MSI | Closed | User Story | Carl Chalmers
483412 | Add crosshair model toggle | Closed | User Story | Carl Chalmers
483414 | Add Phi3 instruct model and RAG for Q&A | Closed | User Story | Carl Chalmers
483418 | Read/write to Azure Storage for local processing | Closed | User Story | Carl Chalmers
490042 | Added real-time data processing | Closed | User Story | Carl Chalmers
502078 | Add light and dark theme | Closed | User Story | Carl Chalmers
502080 | Add biodiversity report export tool | Closed | User Story | Carl Chalmers
503525 | Port 'Layer Cake' viz engine to Rust | Closed | User Story | Cristian Berrogorry Llano
503526 | Texture atlas for embeddings visualization | Closed | User Story | Cristian Berrogorry Llano
503527 | Declarative scene descriptor w/ Salsa diffing | Closed | User Story | Cristian Berrogorry Llano
503528 | Embeddings extraction CLI (DINO + tiny-imagenet) | Closed | User Story | Cristian Berrogorry Llano
503529 | Reviewed event API (Redis-backed) | Closed | User Story | Cristian Berrogorry Llano
503530 | Sequential inference filter refinement | Closed | User Story | Cristian Berrogorry Llano
503531 | Image thumbnail API optimization | Closed | User Story | Cristian Berrogorry Llano
503532 | Fire localization endpoint | Closed | User Story | Cristian Berrogorry Llano
503533 | Fix Redis Lua script index naming bug | Closed | User Story | Cristian Berrogorry Llano
503638 | Technical guidance for codebase finalization | Closed | User Story | Bruno Demuro Segundo
503639 | Drive release readiness - compliance | Closed | User Story | Bruno Demuro Segundo
503640 | Support live camera processing integration | Closed | User Story | Bruno Demuro Segundo
505026 | Add OWL to Sparrow Studio | Closed | User Story | Carl Chalmers
PYTORCH WILDLIFE EXPANSION (#481203) - Features & Stories
DevOps ID | Title | State | Type | Assigned To | Sprint
483369 | Pytorch-Wildlife Base Development | Active | Feature | Zhongqi Miao
483370 | Pytorch-Wildlife Compliance and Logistics | Active | Feature | Zhongqi Miao
483371 | Pytorch-Wildlife Marketing & Comms | Active | Feature | Zhongqi Miao
483381 | Pytorch-Wildlife Bioacoustics | Active | Feature | Zhongqi Miao
503561 | Prototype human-painted iSTFT mask tool | Closed | User Story | Cristian Berrogorry Llano
503562 | Research audio source separation models | Closed | User Story | Cristian Berrogorry Llano
503563 | EXPERIMENT: training from iSTFT annotations | New | User Story | Cristian Berrogorry Llano
503564 | PLAN: Automatic model training loop | Closed | User Story | Cristian Berrogorry Llano
503565 | PROTOTYPE CORE: Automatic model training loop | Active | User Story | Cristian Berrogorry Llano
503566 | PROTOTYPE LOCAL EXECUTION: Auto training loop | Active | User Story | Cristian Berrogorry Llano
503567 | PROTOTYPE TDD: Test driven Development | Active | User Story | Cristian Berrogorry Llano
504253 | PROTOTYPE SAM: Leverage SAM for HOL | New | User Story | Cristian Berrogorry Llano
PYTORCH SPARROW DASHBOARD (#430249) - Features & Stories
DevOps ID | Title | State | Type | Assigned To | Sprint
430244 | Software Development - Client | New | Feature | Carl Chalmers
430245 | Logistics + Promotion + Communication | New | Feature | Bruno Demuro Segundo
430246 | Logistics + Promotion + Communication | New | Feature | Zhongqi Miao
430247 | Software Development - Server | New | Feature | Carl Chalmers
430248 | Legal | New | Feature | Bruno Demuro Segundo
486967 | Create video of updated PYTORCH UI | New | User Story | Pedro Costa Galiana

## Legacy Backlog Items
SPARROW
1 | Do acoustic device model for the Amazon | Running on production in Colombia
Install in Peru (los Amigos)
Create MESH Network. SPARROW/ROBIN XBee support
Remove the need for drawing on top of the picture, and change this to be stored in the metadata in the picture vs actual jpg
We need to assemble SPARROW for Ignite
We need to have SLALOM assemble and deploy SPARROW in WA State
CONDOR
Have CONDOR system available for AlertCalifornia to use, get alerts, get feedback from them
Do actual alignment of cameras (?)
SPARROW API intergration with CalFire insights system (is this done?)
Priority | Description | Comments | Lead | Status
1 | Run fire detection server side for CAL FIRE | How much trust/far are we from this? | Daniel/Miao? | Done
2 | Create a master installation - instruction as very detail list of TO-DO |  | Carl/Bruno | On Track
3 | Do acoustic device model for the Amazon | Can we have this running by end of August? | Daniela | Done
4 | Run SPARROW from Azure |  | Carl | Done
5 | Sourcing and logistics for Jane Godall's institute |  | Bruno | Done
6 | Sourcing and Logistics for SALONGA&VIRUNGA |  | Bruno | Done
7 | Have Acoustic data anomaly detection to be used as camera trap |  | Daniela
8 | Install in Peru (los Amigos) | UPDATE: Probably end of AUG | Bruno/Andres | Delayed
9 | Create MESH Network. SPARROW/ROBIN XBee support |  | Carl | On Track
10 | Remove the need for RTC battery |  | Carl/Bruno | Pospone
11 | Install SPARROW in a bouey (WATER SPARROW) |  | Manolo/Carl/Bruno | Pospone
12 | Remove the need for drawing on top of the picture, and change this to be stored in the metadata in the picture vs actual jpg |  | Carl | Done
13 | Coordination of instalation of the other 2 units in Colombia for SINCHI | Done | Bruno/Andres | Done
14 | El Silencio + Monos Retrofit - Colombia | Done | Bruno/Andres | Done
15 | Automatic PTZ tracking | Important for CalFire and model performance | Carl | Done
16 | SPARROW API intergration with CalFire insights system | Insights platform (Aug/Sept). Works on JSON payload, waiting for Multipart form. | Carl | Done
17 | Fire location triangulation | Researching options, viewpoint/lidar intesection might work | Miao/Bruno/Carl | Done
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wouldn't touch this with the current hardware configuration, since the microphones are far from the cameras
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to try and test, right now we need it to keep SSL and HTTPS
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to wait untill ROBIN is ready
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wouldn't touch this with the current hardware configuration, since the microphones are far from the cameras
Note on D41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to try and test, right now we need it to keep SSL and HTTPS
Note on D42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to wait untill ROBIN is ready